## Sheet1
Date Inserted | Risk | Likelihood | Severity | Control Measure | Revisit 15/06/2021 | Revisit 21/05/2021 | Comment
2021-06-06 | Being able to build the frontend of the application in Angular | Low | Low | I could always create a simple frontend in ASP.Net. Also, I have my work from project 1 to refer back to | This is of no issue. Using my frontend from poroject 1 as a guide, I have been able to create my frontend for this project | No change
2021-06-06 | Failing at getting the all the services to communicate on the web | Medium | High | If getting the services to communicate does prove difficult, I would need to refer to a combination of YouTube videos, speaking to SME's at Avanade and the QA instructors. if worse comes to worst, I could always demo the project locally. Based on project 1 this is easily achieved. | Severity of risk and likelihood remains the same. However, my current research suggests using containers will make the process of getting the services to communicate easier. | Likelihood of risk has dropped to a LOW. I now have the services deployedin the cloud and communicating with each other on the web | 06/06/21: Testing the project on localhost is truly unacceptable and would be my last resort.
2021-06-06 | Being unable to integrate testing into my automated CI/CD pipeline | Low | Medium | Locally run the test and push the test report to my project repo (manual and very repetitive). Seek assistance from Dara. | No change | Managed to integrate the testing instructions to my GitHub Actions | 21/06/2021: Managed to find a third perty GitHub Action program that made it easy to implement
2021-06-06 | Being unable to deploy the services | Medium | High | Begin the project by implementing only the MVP version of the application and focus the bulk of my time on the deployment of the application. Start the project early, ideally the weekend of whenever the project spec is officially released. | Likelihood of risk has increased to HIGH. Even by starting early, I am still usnure as to how I intend deploy my application. The only saving grace is we are yet to learn some of the tools that should help with the deployment e.g. Terraform and Ansible | Managed to deploy my application through using GitHub Actions, Terraform, Ansible and Docker | 06/06/21: Was not able to deploy my Scientia application in project 1
2021-06-06 | Being unable to found a Card Against Humanity API to provide my application with the questions and answer cards it needs. | Low | Low | If an API does not exists, I can create mine. | Severity of risk and likelihood remains the same. Had to create my own API that supplies my application with the card against humanity cards. | No change | 15/06/21: API was created using Node JS
2021-06-15 | Being unable to containerise my application using docker | High | High | Have a session booked with Aaron in which he would guide me through the basics of using docker to containerise application. Dara is also happy to provide me with some assistance when I get stuck with Docker. Also, I have the options of reverting to App Services if Docker gets to difficult. | No change | Severity of risk remain HIGH but likelihood has now fallen to LOW. Managed to run conatiners locally and also deploynand run it on a remote VM through a bash script | 15/06/2021: Need to make my decision regarding sticking with Docker or switching to App Service early enough to deploy the services to App Service successful